## Slide 1: SOFTWARE PROJECT MANAGEMENT AND COST ESTIMATION

## Slide 2: Communication
Training
Intercommunication
Effort increases as:
n(n – 1)/2
3 workers require three times as much pair-wise intercommunication as 2; 4 workers need 6 times as much as 2.
Notes: Communication is in two parts: training and intercommunications
Training is required: in the technology, the goals of the project, the overall strategy and the plan of work. Training cannot be partitioned each new man must go through it individually.
Intercommunication is required in more complex tasks such as software engineering. It assumes that to complete the task workers must have pairwise communications.
If each part of the task must be separately co-ordinated with every other part the effort required increases in a complex way.
Software construction is inherently a team effort and the communication time required is one that cannot be ignored and quickly dominates any partitioning strategy and project costing.

## Slide 3: Improving communication
Use hubs to cut down communication overhead
Examples
  Specification/design documentation
  WiKi
  Development meetings
For all these the communication overhead goes up as N not N^2

## Slide 4: Brooks Experience
1/3 planning
1/6 coding
1/4 component and prototype testing
1/4 system test (all components in hand)
Notes: The first question is what are we guessing at … well it’s time. More particularly, it is time to write some standard number of lines of code, or some function (as a subroutine or sub-process). This is fearsomely complicated because it involves target language, methodology, skills involved, learning required, etc. etc.
Another problem is, what is the goal. Is it the completed prototype?, the alpha release (alpha-1 is considered the first field testable version), or the beta release (beta-1 is the first released version).
Brooks, in MMM presents his rules of thumb for scheduling a software task as about half on debugging of completed code and about 1/6 on coding (the bit which is easiest to estimate).
Planning is given 1/3 of the total time, however, he notes that this does not include research time or exploration of new techniques. Where the learning curve is steep (e.g. in honours projects ? This part can consume more than 50% of the time and lead to nothing being delivered …)
The other key point of experience is that failure to allow enough time for testing is particularly disastrous. Because, this comes at the end of the schedule near the delivery milestone, slippage affects customers and badly reflects on the project as a whole.
We thus see the tricky balance between design at the beginning taking too much time – and full system testing at the end.

## Slide 5: Brookes law
"Adding manpower to a late software project makes it later."
Exceptions
  Applies to projects late already only
  Using modern development techniques reduces communications overhead:
    Continuous integration, test first design, design patterns
  Highly decoupled projects with clear modular specifications

## Slide 6: Experience/techniques for smaller projects
Rudy Rucker teaches software engineering computer games at SJSU
He advises
Estimate how long planning will take
Multiply that time by 3
Use the “Inventer Lifecyle” to generate an Alpha 1 by ~½ way through the project
Notes: Rudy Rucker (San Jose State University) graduate level course. His book (“Software engineering and computer games”, 2003, Addison-Wesley Pearson Education Ltd) is a good one if: a) you are a student; b) you are embarking on a software project to be completed with about 2-3 man months of effort (i.e. roughly an honours project); c) you are planning to write software games.
Rucker develops Brooks idea of using a 1/3 of the time for planning, by suggesting that planning the architecture (essentially the user interface – which we will return to later in the module) should be the goal. He notes that time spent on good architecture will save time in coding and debugging.
He also suggests not doing the waterfall thing, nor really the spiral thing, but a much more concrete thing based on producing small field releases until a final design and feature freeze can happen.
The calls this the “Inventor Lifecyle” … but note this is for students on short 1 to 4 man projects.

## Slide 7: Inventor Lifecyle (one/two person projects)
COMP319 Software Engineering II
Requirements gathering
Beta N program and User Guide
Architecture
Alpha N program and User Guide
Final design and feature freeze
Testing and debugging beta N
Specification N and detailed design N
Final version and product ship
Rucker (2003) p39

## Slide 8: Cost Estimation Research
100s of papers since the 1960s
As development techniques improve e.g. OO, cost estimation has to adapt
Move from
  Coding estimation
Move to
  Functional estimation

## Slide 9: Cost estimation approaches
Expert estimation
  Planning poker
  WBS
Formal estimation
  COCOMO
Combined methods
  Each formal estimation technique has a expert phase anyway

## Slide 10: Other approaches
Case based reasoning
  Using many previous projects/coding efforts to estimate this project
Lexical analysis of requirements specifications

## Slide 11: Planning poker
Each member of planning team given pack of cards with numbers on
Project manager introduces project
  Team clarifies assumptions
  Discuss risk
Each member picks a card as estimate
Lowest and highest estimation members given change to justify decision
Discuss, then go back to 3, until consensus reached

## Slide 12: Planning poker benefits
Reduces anchoring
  Low anchor
    “"I think this is an easy job, I can't see it taking longer than a couple of weeks”
  High anchor
    “I think we need to be very careful, clearing up the issues we've had in the back end could take months”
Studies
  Molokken-Ostvold, K. Haugen, N.C.
Notes: Molokken-Ostvold, K. Haugen, N.C. (13 April 2007). "Combining Estimates with Planning Poker--An Empirical Study". IEEE
This showed the planning poker technique produced estimates were less optimistic and more accurate than estimates obtained through other approaches such as mechanical combination of individual estimates for the same tasks.

## Slide 13: Software productivity metrics
Measures of size
  Lines of (source) code per person month: (LOC/pm)
  Object code instructions
Document pages
Measure of function
  Function points
  Object points

## Slide 14: Lines of code (KLOC)
Easy to measure
Difficult to estimate
As productivity measure?
  Code quality
  Project delivery
  Language dependency

## Slide 15: Estimating lines of code
Structural decompose project into separate modules
Get programmer to produce 3 figures for each module
  pessimistic estimate of LOC for module
  average estimate of LOC for module
  optimistic estimate of LOC for module
Use weighting factor based on previous estimation performance

## Slide 16: System Development times
 | Analysis | Design | Coding | Testing | Documentation
Assembly code | 3 | 5 | 8 | 10 | 2
High level language | 3 | 5 | 4 | 6 | 2
 | Size | Effort | Productivity
Assembly code | 5000 lines | 28 weeks | 714 lines/month
High level language | 1500 lines | 20 weeks | 300 lines/month

## Slide 17: Function points
Estimates of the program feature elements
  External input and output
  User interactions
  External interfaces
  Files used

## Slide 18: Calculating Function points
slide 18
3SFE519 S Coope 2004
x Weighting factor
User
input count
3
4
6
User
output count
4
5
7
User
inquiries
3
4
6
Number of
Internal logical files
7
10
15
External
Interface files
5
7
10
Simple
Average
Complex
Count total

## Slide 19: Function point analysis
Internal logic file
  tables in a relational database
  Xml files used in application
  Complexity : record types, data element types (e.g. surname, post code)
External interface file
  Same as ILF but not maintained by application
User input
  Usually user input screen
  Complexity : data element types and file type referenced (e.g. count of tables updated)

## Slide 20: Function point analysis
External outputs
  Data presented to the user
  Some mathematics or derived data obtained
  Complexity measure:
    data element types and file type referenced (e.g. count of tables updated)
External enquires
  Data presented to the user
  No maths or derived data involved
  Complexity measure : see external output

## Slide 21: Function point estimation including the value adjustment factor (VAF)
FP = count-total x (0.65 + 0.01 ∑Fi)
F1 = Reliable backup and recovery (1-5)
F2 = Data communications (1-5)
F3 = Distributed functions (1-5)
F4 = Performance (1-5)
F5 = Heavily used configuration (1-5)
F6 = Online data entry (1-5)
F7 = Operational ease (UI) (1-5)
F8 = Master file updated online (1-5)
F9 = Complex interface (1-5)
F10 = Complex processing (1-5)
F11 = Reusability (1-5)
F12 = Installation included (1-5)
F13 = Multiple sites (1-5)
F14 = Facilitate change (1-5)
Notes: Note this is often not used. The VAF will adjust the raw FP count by a factor of about 2 either way. In general function point tool use the raw FP count. From devdaily.com/FunctionPoints
“I can't tell you much about the history of the VAF, but what I can tell from the conversations I've had with many other users is that they don't use the VAF. This stems from at least two reasons that I can determine:
Most users count function points to derive a number that they can plug into another piece of software to determine a cost estimate. Those other software applications usually have their own equivalent of the VAF, and in fact, instruct you to supply the ``raw FP count''. So, in this case, the VAF competes against these vendor tools.
Some users don't feel that the GSCs are flexible enough. I tend to agree, and I think it's an easy argument. When you look at the math below, you'll see that for two applications under consideration, if both start with the same function point count - let's say 1,000 FPs - after adjustments the hardest application in the world would be rated at 1,350 FPs, and the easiest possible application would be rated at 650 FPs when adjusted. Let's say the hardest application in the world had to run on 10 different operating systems in 15 languages and be distributed electronically to 1 million users, and the easiest would be written in Microsoft Access, run on Windows, and be used by only one user, the author of the program. Do you really think the first application is only about twice as hard to deliver as the second? No, I certainly don't, and this is why I don't use the VAF.”