## Slide 1: SOFTWARE PROJECT MANAGEMENT AND COST ESTIMATION

## Slide 2: Object points (function + code)
Count number of
  screens
  reports
  3GL components (Java, C++ classes)
For each use following weighting based on complexity
Object type simple Media Difficult
Screen 1 2 3
Report 2 5 8
3GL components 10

## Slide 3: Function points verses Object points
Function points
  Established standard
  Much legacy estimation data available
  Supported by many tools
  Can be calculated very early on, requirements stage
Object points
  Newer
  Easier to calculate
  Provides allowance for re-use

## Slide 4: Cost Estimation
From size estimation (FP, OP or KLOC)
Map to cost using cost estimation model
Two error factors
  Original estimation error
  Cost derivation error
Or
Use direct estimation
  E.g. poker planning

## Slide 5: Factors affecting productivity
Application domain experience
Process quality
Project size
Technology support
Working environment
Notes: Individuals in a project may vary in their productivity by a factor of 10 (Boehm, et al. 1995), that is from 4 object points per month to 50.
The composition of the team and other factors must be taken into consideration in the overall estimate being made.
These other factors are:
Knowledge of the application domain
The software process used in development – if these are good productivity is higher (we return to this later)
Large projects need communication with less time for development and high productivity
Good CASE tools, configuration management system etc improve productivity
Quietness and private areas contribute to better productivity

## Slide 6: Estimation techniques
Algorithmic cost modelling e.g. Constructive Cost Modelling (CoCoMo)
Expert judgement
Estimation by analogy
Parkinson’s Law
Pricing to win
Notes: Using historical cost information an equation is developed that relates some software metric (usually size) to cost. Estimates of the metric then predict the cost/effort required.
Multiple experts estimate, then discuss and agree a compromise cost.
The cost of new project is estimated by analogy with comparable completed projects.
Parkinson’s Law: work expands to fill the time. If there are 5 people and the software must be delivered in 6 months then the effort estimate is 30 person months.
The customers budget determines the cost. Makes sense if the system can be shipped to a subsequent customer.
However, most methods assume that will be no significant changes in the way software development is done. Changes in the past 10 years have shown that this is not a safe assumption. Examples of changes that affect estimation include:
Distributed and grid based systems
Web facilities
Entity Resource Planning or db centred systems
Shrink wrapped software
Module reuse
Scripting facilities
CASE tools

## Slide 7: Constructive Cost Modelling (CoCoMo)
Notes: Constructive Cost Modelling (COCOMO) is an algorithmic model that is well known, widely used as a commercial tool, and software for it is in the public domain.
It was first proposed by Boehm, B. in his 1981 book “Software engineering economics”, Prentice-Hall. The definitive book for the method is Boehm, B. (2000) “Software Cost Estimation with COCOMO II”, Prentice-Hall.
Summary of the COCOMO II method is in the paper Boehm, B., Clark, B. et al. (1995) “Cost models for future software life cycle processes: COCOMO II”, Annals of Software Engineering, Vol 1, p57-94.
COCOMO assumes a stable software house or software department for which historical measures of software productivity exist. Where this is not available, the published data from finished software projects may be used.
In 1981 COCOMO was based on the waterfall model using a programming language. Now, it can cope with changes in method (e.g. the spiral or incremental model etc), use of shrink wrapped components such as Oracle that provides both a DBMS and full database programming language, and the use of various CASE tools and hardware.

## Slide 8: Algorithmic cost modelling
Assumes there is mathematical relationship between
  Measure of size of project and how much effort it takes
  Uses data from many projects to produce model
  Tries to take into account variations in input factors

## Slide 9: Algorithmic cost modelling research
Take a series of projects
Make estimations at begin and part way through
  Total size
  Complexity
  Re-use factors
Measure how long the project takes in person months
Try and correlate these 2 taking into account both factors

## Slide 10: Problems with algorithmic cost modelling
Development approach change
Estimation of project size and complexity is difficult
Model cannot take into account all factors
  Development and testing approach
  Regressive development way overrun time

## Slide 11: COCOMO
Barry W. Boehm 1981
63 projects at TRW Aerospace
From 2,000 to 100,000 lines
COCOMO II 2000
  University of Southern California
  University of California Irvine
  COCOMO™ II Affiliates' Program

## Slide 12: The COCOMO method
Input
  Conduct of the project (e.g. design model)
  Staff available
  Hardware and CASE tools involved
  Nature of the product
Output estimates
  Size of the system (LOC and function points)
  Project schedules and team factors
  Cost and staffing profiles.

## Slide 13: (1) Application Composition
Application composition
  For: prototype system using scripting, SQL etc.
  Uses: object points
PM = (NOP x (1 - % reused/100)) / PROD
PM : Person months
NOP: Total number object points
PROD : Object point productivity (4 low 50 high)
Notes: We can see from this that again there is a lot of estimation, it has to for example make use of the % of reused code.

## Slide 14: (2) Early Design
Early design
  For: initial effort estimation
  Uses: function points
  Effort = A x SizeB x M
  A : constant, found to be about 2.94
  Size : thousands of lines of code (derived from SLOC)
  B : measure of product novelty
  M: product of 7 values each between 1 to 6
Notes: Early Design model
Used once the requirement is finalised and an architecture design is required with an estimate of cost. It is based on the
formula:<read>
A is a constant which based on Boehms data is 2.94; The size is thousands of lines of source code : KSLOC – obtained by calculating the function points required (there are look-up tables to do the relationship between function points and KSLOC).
The exponent (B) varies from 1.1 to 1.24 and covers an estimate of the novelty of the project. As novelty increases the number of lines of code and thus effort increases.
The constant M is the product of seven project and process characteristics measured on a scale from 1 (very low) to 6 (very high).
RCPX product reliability and complexity
RUSE reuse required
PDIF platform difficulty
PERS personnel capability
PREX personnel experience
SCED schedule
FCIL support facilities.
From this we get:
PM = 2.94 x Size**B x (RCPX x RUSE x PDIF x PERS x PREX x SCED x FCIL)

## Slide 15: Re-use model (auto gen code)
Reuse - variant (A)
For: integration projects using reusable or automated code generation
Uses: lines of code reused, or generated
For automatically generated code:
PM = (ASLOC x AT/100) / ATPROD
Notes: Reuse Model (A)
Two variants exist based on whether all code is automatically generated (A) or some is automatically generated and some newly written (B).
Reuse of code is perhaps best illustrated in computer game software, where new story lines lead to new games – e.g. Harry Potter.
Code that does not need to be understood to reuse it is termed black box code, and the development effort associated with it is deemed to be zero.
ASLOC = Adapted Source Lines of code
Code that has to be modified to be reused, is termed white box code, and effort is required to understand and modify it.
In addition code may be automatically generated – adding a second form of reuse.
PM = person months
(A) For code automatically generated the formula used is:
ASLOC is the number of lines of code in the component that have to be adapted. AT is the percentage of adapted code that is automatically generated and ATPROD is the integration productivity of staff. ATPROD is currently assumed to be about 2,400 source statements per month (Boehm et al., 2000).
e.g. If there is a total of 20,000 lines of white-box reused code in a system and 30% is automatically generated, then PM(auto) is: (20,000 x 30/100) / 2400 = 2.5 person months.

## Slide 16: Re-use model (new code)
Reuse - variant (B)
Where new written code is required:
ESLOC = ASLOC x (1 – AT/100) AAM
Estimate of error for new code
Notes: Reuse Model
(B) In the reuse model where there is some new code and some reused code, the effort required is calculated indirectly. Thus, based on the number of lines of code reused, it calculates a figure that represents the number of lines of new code.
e.g. With 30,000 lines of code to be reused, the new equivalent size estimate might be 6,000; or put another way 6,000 new lines are required to reuse the 30,000. This calculated figure is added to the number of lines of new code to be developed in the COCOMO II post-architecture model.
The estimates in this reuse model are thus:
ASLOC – number of lines of code in the component that have to be adapted
ESLOC – equivalent number of lines of new source code
The ESLOC figure summarises the effort required in making changes to the reused code and for making changes to the system to integrate the code. It also takes into account the automatically generated code where the calculation is as above.
We now can calculate the equivalent lines of source code as: <read>
ASLOC is reduced according the the percentage of automatically generated code.
AAM – Adaptation Adjustment Multiplier. A sum of: the cost of making the changes, cost of understanding the code, and an assessment factor which determines whether the code can be reused.
This model is non-linear, as more and more reuse is contemplated, the cost per code unit reused drops.

## Slide 17: Post-architecture
For: overall development effort
Uses: number of lines of source code
PM = A x SizeB x M
Notes: Post-Architecture Model
Once an initial architectural design is available and the structural units are known the post-architectural COCOMO II model can be used. It uses the same exponent based formula seen before: It is assumed this will now be more accurate and uses a more extensive set (17) of product, process, and organisational attributes as more information is now available. The model uses an estimate of:
the total number of lines of new code to be developed;
the equivalent number of source lines of code (ESLOC) needed calculated using the reuse model and
3. the number of lines of code that have to be modified because of changes in the requirements.
These values are added to give KSLOC. B (which is continuous, as before) is made up of 5 scale factors rated on a six point scale from very low to extra high (5 to 0). The ratings are summed and divided by 100 and added to 1.01 to get the actual exponent used. The factors cover: the previous experience with this type of project – a new project scores low (say 4); freedom from client involvement – no client involvement rated very high (say 1); risk analysis done – no risk analysis rated very low (say 5); team cohesion and experience of working together – rated nominal (say 3); and process control maturity – some process control present, rated nominal (say 3).
In this example the sum is 16 which we divide by 100. Add 0.16 to 1.01 to give a value for B of 1.17. M is calculated using 17 project cost drivers covering the product, the hardware, personnel, and the project (7 covered earlier). The are estimated based on experience and in practice are difficult to use with any accuracy.

## Slide 18: Project duration and staffing
Calendar time (TDEV) can be calculated: TDEV = 3 x (PM) (0.33+0.2*(B-1.01))
  Where PM is the effort computation and B the exponent as computed earlier.
Staffing (PM) estimates are affected by the communication problem, and as noted before, is not linear.

## Slide 19: Summary
Cost Estimation Modelling
  Relies on expert judgement
  Requires much effort
  Produces subject results
Alternatives
  Group estimation
  Analogy estimation
  Pricing to win